## Epic
Epic Name:
Epic Value Statement
For | residents of the City of Peoria, IL
who | travel about the city for work and/or recreation
the | Working As Designed project
is a | interactive, technology system
that | provides a mechanism for awareness of current and planned infrastructure projects that effect them.
Unlike | the current, distributed means of getting this information via door hangers, newspaper, TV, radio, social media, little yellow signs,
our solution(product) | provides this information all in one place when and where the residents need it.
This supports our company strategy to | <>. <<insert name or description of strategy>>.
Scope
In Scope: | - Opportunity for residents to collaborate on priorities of projects - Project information sourced from contractors, Public Works - Permits, Public Works - Project Management, residents (new projects), crowd-sourced live data - Configurable notifications (subscriptions) - Visualization (maps) - Mobile app - Construction site kiosk - Project status (plan change reasons) -
Out of Scope: | - Eddystone beacons (out for Gen 1) - Using Google to make project publicly available - Web application - Contractor project update interface - Text notifications - Email notifications -
Success Criteria: | - Meets Challenge (30%) How well does the product communicate construction projects? How accessible is it to the public? How engaging is it to use? - Quality (30%) How well does it work? Is it dynamic? How clean/well-documented is the code? - Creativity (20%) How creative is the solution? How ambitious is the project? - Experience (20%) Is the product aesthetically pleasing? Is the product easy to navigate?
Nonfunctional: | - Ease of use - Easy to do business with - Less than 3 clicks to get what you want - -

## Personas
Residents
Business owners
Visitors
Construction companies | Contractors

## Project Types
Street
Sidewalk
Water
Parks
Lights
New
Trash
Animal Control
Private utilities | Cable | Fiber | Phone
Flood
Tree
Special events
Traffic Accidents
Emergency
Police
Fire

## Features
ID | Feature | Benefit | Acceptance Criteria | User ¦ Business Value | Time Criticality | RR ¦ OE Value | CoD | Size | WSJF | Status | Notes | Team(s)
1 | Plot infrastructure projects on a map by location | Visualize location of ongoing construction projects and potential traffic impacts | - Given project exists in a location, when it is plotted, then the user can see it on a map - Map loads in less than 3 seconds - | 5 | 8 | 1 | 14 | 3 | 4.6667 |  |  |  | Y
2 | User feedback widget | Allows residents to provide verbal or image feedback on the progress of a project | - Given the user provided feedback, when it is submitted, then the user receives a email confirmation - Links to PubWorks system - Allows users to create profiles |  |  |  | 0 |  | 0 |  |  |  | N
3 | Text / email notifications for new or changed project status | Receives latest information impacting resident | - Given the user has subscribed to certain project, when the status of the project changes, then a text/email notification is sent to the user. - Allows users to create profiles - |  |  |  | 0 |  | 0 |  | Out of scope for Gen 1 |  | N
4 | Favorite projects | Allows residents to select projects they are interested in tracking | - Provides project selection configuration - - |  |  |  | 0 |  | 0 |  |  |  | Y
5 | Define locations of interest | Allows residents to select a place or route they want to track | - Provides point-radius configuration - Provides route (A to B, round-trip, etc.) tracing configuration - |  |  |  | 0 |  | 0 |  | Out of scope - Polygon location |  | ?
6 | Project summary | Describes the project: includes current status, planned completion | - Current status - Planned completion - Contractor name - User feedback - comments, images - |  |  |  | 0 |  | 0 |  |  |  | Y
7 | Alternative routes | Provides alternative to favorite route if project impacting time to destination | - Given a favorite route is configured, when a project new or changes impacts the time to destination, then propose an alternative route - Google Maps API? - |  |  |  | 0 |  | 0 |  |  |  | N
8 | New project proposal | Allows residents to submit project proposals to the city | - Comments - Images - |  |  |  | 0 |  | 0 |  |  |  | N
9 | Project proposal voting | Allows residents to endorse project proposals | - Allocation of virtual dollars - - |  |  |  | 0 |  | 0 |  |  |  | N
10 | Filter projects | Allows user to include/exclude project types | - Infrastructure projects - Events - …List project types |  |  |  | 0 |  | 0 |  |  |  | Y
11 | Include auto and bike routes | Provide information for both automobile drivers and bikers | - | [9 empty] | N
12 | Entry point - Map centered on your location | Start where the user is at | - List of latest project updates prioritized by favorites, then timestamp, then proximity | [9 empty] | Y
13 | Tutorial | Walk user through using the app | [8 empty] | Gen 1 - A list of features |  | Y-L
14 | User profile screen | [11 empty] | N
15 | Beacon - URL notification | [9 empty] | Next gen |  | N
Leffingwell et al. © 2014 Scaled Agile, Inc.

## Stories
ID | Type | Feature | Story Title | Story | Acceptance Criteria | Priority | Size | Status | Notes | Team
|  |  |  | As a <user or role> I can <do something> so that <value received> | - - -
- - -
- - -
- - -
- - -
- - -
- - -
- - -
- - -
- - -
Leffingwell et al. © 2014 Scaled Agile, Inc.

## Story
Story Title:
User Story
As a | <user or role>
I want | <do something>
so that | <value received>
Story Title:
User Story
As a | <user or role>
I want | <do something>
so that | <value received>
Story Title:
User Story
As a | <user or role>
I want | <do something>
so that | <value received>

## Story 2
|  | <user or role> | <do something> | <value received> |  |  | <user or role> | <do something> | <value received> |  |  | <user or role> | <do something> | <value received>
Story Title: | User Story | As a | I want | so that | Story Title: | User Story | As a | I want | so that | Story Title: | User Story | As a | I want | so that

## Acceptance Criteria
Story Title:
Acceptance Criteria
Story Title:
Acceptance Criteria
Story Title:
Acceptance Criteria

## Acceptance Criteria 2
| Acceptance Criteria |  | Acceptance Criteria |  | Acceptance Criteria
Story Title: |  | Story Title: |  | Story Title:

## WSJF
Weighted Shortest Job First (WSJF)
Field Descriptions
𝑼𝒔𝒆𝒓−𝑩𝒖𝒔𝒊𝒏𝒆𝒔𝒔 𝑽𝒂𝒍𝒖𝒆 | Do our users prefer this over that?
What is the revenue impact on our business?
Is there potential penalty or other negative impact if we delay?
𝑻𝒊𝒎𝒆 𝑪𝒓𝒊𝒕𝒊𝒄𝒂𝒍𝒊𝒕𝒚 | How does the user/business value decay over time?
Is there a fixed deadline?
Will they wait for us or move to another solution?
Are there milestones in the critical path impacted by this?
𝑹𝒊𝒔𝒌 𝑹𝒆𝒅𝒖𝒄𝒕𝒊𝒐𝒏¦𝑶𝒑𝒑𝒐𝒓𝒕𝒖𝒏𝒊𝒕𝒚 𝑬𝒏𝒂𝒃𝒍𝒆𝒎𝒆𝒏𝒕 | What else does this do for our business?
Does it reduce the risk of this or a future delivery?
Is there value in the information we will receive?
Will this feature open up new opportunities?
WSJF
WSJF =(𝑈𝑠𝑒𝑟−𝐵𝑢𝑠𝑖𝑛𝑒𝑠𝑠 𝑉𝑎𝑙𝑢𝑒 + 𝑇𝑖𝑚𝑒 𝐶𝑟𝑖𝑡𝑖𝑐𝑎𝑙𝑖𝑡𝑦 + 𝑅𝑖𝑠𝑘 𝑅𝑒𝑑𝑢𝑐𝑡𝑖𝑜𝑛|𝑂𝑝𝑝𝑜𝑟𝑡𝑢𝑛𝑖𝑡𝑦 𝐸𝑛𝑎𝑏𝑙𝑒𝑚𝑒𝑛𝑡)/𝑆𝑖𝑧𝑒